CSCI 3038 FINAL PROJECT

Black Box Optimizer

Scope of Work

Authorized work packages, deliverables, exclusions, and acceptance obligations

| Document control | Scope control |
| --- | --- |
| Document ID BBO-SOW-001 | Version Draft v0.1 |
| Prepared July 17, 2026 | Status Draft for team ratification |
| Governing charter BBO-PC-001, Draft v0.1 | Effective date TBD |
| Work assignments TBD | Course requirements Pending publication |

SCOPE COMMITMENT
This Scope of Work authorizes one strictly local, synchronous, sequential MVP. The MVP provides a registry-selected RandomSearch implementation and returns a Pareto Front across multiple declared objectives. Architectural extensibility does not authorize additional algorithm implementations.

## Scope at a Glance

| Scope dimension | Baseline obligation |
| --- | --- |
| Execution | One local worker trial at a time; no networking or concurrency |
| Search | Seeded RandomSearch through Algorithm Registry |
| Objectives | Two or more supported; Pareto dominance with mixed directions |
| Evidence | Immutable TrialRecords and append-only persisted TrialHistory |
| Stopping | Application Controller enforces modular StopPolicy |
| Acceptance | Tests, reproducible demonstration, Pareto fixture, and documented outputs |

# 1. Document Control and Scope Authority

This Scope of Work converts the Project Charter into specific work obligations. It controls what the team will produce and how completion will be demonstrated. The Technical Design Specification will control how the software satisfies these obligations.

| Document | Controlling concern | Current status |
| --- | --- | --- |
| Project Charter BBO-PC-001 | Purpose, authority, vocabulary, governance, and high-level boundaries | Draft v0.1 |
| Scope of Work BBO-SOW-001 | Work packages, deliverables, exclusions, requirements, and acceptance | Draft v0.1 |
| Technical Design Specification | State model, interfaces, schemas, algorithms, and validation rules | Not yet issued |

## 1.1 Scope interpretation

- Only work expressly included in this Scope of Work is part of the MVP baseline.

- An extensibility point does not require every possible extension to be implemented.

- Unknown course artifacts become obligations only after formal incorporation through change control.

- A conflict among controlling documents must be reconciled; it must not be resolved through an undocumented assumption.

- Team ownership remains TBD until the work-package allocation is ratified.

## 1.2 Approval and revision record

| Authority | Decision | Date | Revision condition |
| --- | --- | --- | --- |
| Project team | Pending | TBD | Approves baseline work and later material changes. |
| Course instructor | Requirements pending | TBD | May introduce course-specific artifacts or constraints. |

# 2. Shared Vocabulary and Controlling Definitions

CONTROLLED VOCABULARY
These definitions are intentionally repeated from the Project Charter so this Scope of Work can stand alone. The same definitions will govern the Technical Design Specification.

## 2.1 Optimization and result terms

| Term | Controlling definition |
| --- | --- |
| Algorithm Registry | The approved mapping from an algorithm name in AlgorithmSpec to a SearchAlgorithm implementation. The MVP contains RandomSearch; arbitrary external plugin loading is excluded. |
| AlgorithmSpec | An immutable selection of one registered search algorithm and its algorithm-specific settings. A random seed belongs here rather than in OptimizationContract. |
| Candidate Configuration | One complete, legal set of parameter values proposed for a single worker trial. It is an intended input, not a completed result. |
| Dominance | The relationship in which Trial A is no worse than Trial B on every objective and strictly better on at least one objective after applying each direction. |
| Eligible Trial | An execution-successful TrialRecord containing a finite numerical value for every objective required by OptimizationContract. |
| Metric | A named finite numerical value written by the worker. It becomes an objective only when declared by OptimizationContract. |
| Minimum Viable Product (MVP) | The smallest complete baseline: local sequential execution, registered RandomSearch, multiple objectives, Pareto-front output, persistence, and reporting. |
| Objective | A named metric and direction—minimize or maximize—used to compare eligible trials. |
| OptimizationContract | The immutable, algorithm-independent definition of the parameter space and objective set. |
| Optimization Result | The final structured result containing the ParetoFront, termination reason, and completed TrialHistory snapshot. |
| Parameter | A named input value sent to the worker for one trial. |
| ParameterDefinition | The immutable declaration of a parameter's name, type, and legal domain. MVP types are integer, float, and categorical. |
| Pareto Front | The set of eligible TrialRecords not dominated by any other eligible TrialRecord. It is a set of trade-offs, not an automatically selected winner. |
| ProposalResult | An explicit algorithm response containing either a Candidate Configuration or a named reason no candidate can be proposed. |
| RandomSearch | The first registered SearchAlgorithm. It samples legal, untried candidates using a configured seed. |
| SearchAlgorithm | The modular policy interface that proposes the next candidate using OptimizationContract and read-only TrialHistory. |
| Search Exhaustion | The normal condition in which a SearchAlgorithm cannot produce another legal, untried candidate. |

## 2.2 Execution and lifecycle terms

| Term | Controlling definition |
| --- | --- |
| Application Controller | The deterministic finite-state lifecycle governor that sequences selection, execution, recording, stop evaluation, and finalization. |
| Execution Metadata | Facts observed by the Runner, including runtime, exit code, timeout status, and captured error information. |
| Local Execution | Execution on one local machine using local processes and files; network services and remote workers are excluded. |
| Runner | The component that launches one worker synchronously, applies timeout, and captures Execution Metadata. It does not choose or rank candidates. |
| Sequential Execution | The rule that no more than one worker trial is active and the controller waits for completion before advancing. |
| StopDecision | The explicit result of evaluating StopPolicy, including whether another execution is permitted and any termination reason. |
| StopPolicy | The modular immutable rules governing execution limits and termination conditions. |
| Trial | One attempted evaluation of one Candidate Configuration through the external worker contract. |
| TrialHistory | The append-only ordered collection of TrialRecords for one optimization run; algorithms receive a read-only snapshot. |
| TrialRecord | The immutable record of one attempted trial: exact parameters, parsed metrics, and Execution Metadata. |
| Worker | The opaque external local program being optimized; the optimizer never imports it. |
| WorkerSpec | The immutable operational specification describing invocation, metrics-output path, and per-trial timeout. |

## 2.3 Critical distinctions

| Distinction | Required interpretation |
| --- | --- |
| Candidate vs. TrialRecord | Intended input versus immutable evidence of an attempted execution. |
| Metric vs. Objective | Returned numerical value versus a metric selected for optimization. |
| Execution success vs. eligibility | A completed process may still lack a complete objective vector. |
| Search Exhaustion vs. StopDecision | Algorithm outcome versus execution-policy decision. |
| Pareto Front vs. winner | Non-dominated trade-offs versus an unjustified universal ranking. |

# 3. Scope Statement

## 3.1 Work objective

The project team will design, implement, verify, document, and demonstrate a local Python application that optimizes compliant external worker programs. The application will perform sequential trials, retain immutable evidence, support registry-selected algorithms, and return the non-dominated Pareto Front for multiple objectives.

## 3.2 Required end-to-end outcome

- Load and validate a JSON project configuration.

- Construct WorkerSpec, OptimizationContract, AlgorithmSpec, and StopPolicy.

- Create RandomSearch through the Algorithm Registry.

- Propose one legal, untried Candidate Configuration.

- Authorize and execute one local worker trial synchronously.

- Parse one-row CSV metrics and construct exactly one immutable TrialRecord.

- Append and persist the TrialRecord in TrialHistory.

- Repeat until StopPolicy or Search Exhaustion terminates execution.

- Evaluate eligible TrialRecords through mixed-direction Pareto dominance.

- Return an Optimization Result containing the Pareto Front, termination reason, and evidence outputs.

## 3.3 Demonstration baseline

The baseline demonstration will use a Python worker accepting learning_rate, temperature, and batch_size. It will write accuracy, loss, and training_time so the example contract can maximize accuracy while minimizing loss and training time. Its numerical behavior will intentionally produce trade-offs and multiple Pareto members.

AUTHORITATIVE RESULT
The exported Pareto Front is the optimization result. Visualizations are explanatory views and may not replace or silently scalarize the objective vectors.

# 4. Scope Boundaries

## 4.1 Included capabilities

- Python 3.13.14-compatible command-line application

- JSON configuration and pre-run validation

- integer, float, and categorical parameter domains

- two or more objectives with independent minimize/maximize directions

- built-in Algorithm Registry and AlgorithmSpec

- seeded RandomSearch as the only required search implementation

- local synchronous subprocess invocation using an argument list

- one worker trial at a time and one unique directory per trial

- one-row CSV metrics parsing and finite-number validation

- immutable TrialRecords, append-only TrialHistory, and per-trial persistence

- Application Controller state machine and modular StopPolicy

- maximum trials, per-worker timeout, Search Exhaustion, cancellation, and fatal-error termination

- Pareto-dominance calculation for mixed-direction objectives

- Optimization Result, history export, Pareto export, summary, and visualizations

- demo worker, sample configurations, automated tests, README, and reproducible demonstration

## 4.2 Excluded capabilities

- network programming, remote APIs, remote workers, or hosted services

- multithreading, async execution, process pools, or concurrent candidate evaluation

- distributed execution or multi-machine coordination

- resume-after-interruption or restoration of algorithm random state

- Bayesian, evolutionary, grid, hill-climbing, or other additional search implementations

- dynamic discovery or execution of arbitrary external algorithm plugins

- automatic weighted scalarization or automatic selection of one Pareto winner

- worker imports, source inspection, gradient access, or model-specific hooks

- graphical user interface, web interface, database, authentication, or user accounts

- production hosting, packaging as a service, or operational monitoring infrastructure

# 5. Scope of Work — Work Packages

The following work packages define the baseline work. Ownership will be assigned later; every package requires a primary owner and an interface reviewer before implementation is considered allocated.

| Work package | Primary concern | Owner | Reviewer |
| --- | --- | --- | --- |
| WP-01 | Governance and controlled documentation | TBD | TBD |
| WP-02 | Configuration and immutable domain contracts | TBD | TBD |
| WP-03 | Controller, StopPolicy, and local execution | TBD | TBD |
| WP-04 | Trial evidence, history, and persistence | TBD | TBD |
| WP-05 | Algorithm Registry and RandomSearch | TBD | TBD |
| WP-06 | Multi-objective Pareto evaluation | TBD | TBD |
| WP-07 | Demo worker, reporting, and visualization | TBD | TBD |
| WP-08 | Verification, integration, and handoff | TBD | TBD |

## WP-01 — Governance and Controlled Documentation

Owner: TBD    Reviewer: TBD    Dependencies: Project Charter

Establish and maintain the controlled project baseline so implementation decisions remain traceable and later course requirements can be incorporated deliberately.

### Included activities

- Maintain Charter, Scope of Work, and Technical Design Specification identifiers and versions.

- Record approvals, unresolved requirements, material changes, and ownership assignments.

- Maintain the shared vocabulary identically across controlled documents.

- Translate later instructor requirements into explicit scope or technical changes.

### Required outputs

- Ratified Project Charter and Scope of Work

- Approved Technical Design Specification

- Change record and current work-package assignment matrix

COMPLETION STANDARD
All three controlled documents agree on definitions and boundaries; pending items are labeled rather than assumed.

## WP-02 — Configuration and Immutable Domain Contracts

Owner: TBD    Reviewer: TBD    Dependencies: WP-01 definitions

Implement the validated, algorithm-independent configuration and immutable data objects consumed by the remaining components.

### Included activities

- Define and validate ParameterDefinition, Objective, OptimizationContract, AlgorithmSpec, StopPolicy, and WorkerSpec.

- Load the objects from one JSON project configuration.

- Reject duplicate names, invalid bounds, empty choices, unsupported directions, illegal algorithm settings, and nonpositive limits before trial 1.

- Ensure nested collections cannot be mutated through public interfaces.

### Required outputs

- Configuration loader and validation errors

- Frozen domain models and example JSON configuration

- Unit tests for valid and invalid configurations

COMPLETION STANDARD
A valid example produces all required immutable objects; invalid examples fail before a worker can be authorized.

## WP-03 — Application Controller, StopPolicy, and Local Execution

Owner: TBD    Reviewer: TBD    Dependencies: WP-02 contracts

Implement the deterministic lifecycle that authorizes at most one worker execution and produces an explicit termination reason.

### Included activities

- Implement initializing, selecting, gating, executing, recording, evaluating, finalizing, stopped, and failed states.

- Evaluate StopPolicy before every worker launch and after every appended TrialRecord.

- Invoke workers synchronously with an argument list and without shell=True.

- Apply per-trial timeout, handle KeyboardInterrupt, capture launch failures, and finalize existing evidence.

### Required outputs

- Application Controller and state-transition tests

- Runner subprocess boundary and Execution Metadata capture

- Explicit StopDecision and termination-reason output

COMPLETION STANDARD
No transition permits simultaneous worker trials; every authorized attempt reaches recording or a traceable fatal failure path.

## WP-04 — Trial Evidence, History, and Persistence

Owner: TBD    Reviewer: TBD    Dependencies: WP-02 and WP-03

Preserve exactly what was attempted and observed so search, Pareto evaluation, reporting, and failure analysis consume stable evidence.

### Included activities

- Parse one-row CSV metrics and distinguish parsing validity from objective eligibility.

- Construct one immutable TrialRecord for every attempted execution, including nonzero exit, timeout, launch failure, missing file, and malformed metrics.

- Append TrialRecords in order and expose only a read-only history snapshot.

- Persist flattened history after every appended record without implementing run resumption.

### Required outputs

- TrialRecord factory and TrialHistory

- Trial-specific directories and metrics preservation

- history.csv checkpoint with parameter and metric prefixes

COMPLETION STANDARD
Completed records cannot be rewritten; an interrupted process leaves all previously appended evidence available even though resumption is out of scope.

## WP-05 — Algorithm Registry and Seeded RandomSearch

Owner: TBD    Reviewer: TBD    Dependencies: WP-02 and WP-04

Prove the modular search boundary with one deterministic registered algorithm while avoiding random-search assumptions in unrelated concerns.

### Included activities

- Define SearchAlgorithm and ProposalResult interfaces.

- Construct the selected algorithm from AlgorithmSpec through a built-in registry.

- Sample legal integer, float, and categorical values using NumPy's seeded Generator.

- Avoid previously attempted Candidate Configurations and return explicit Search Exhaustion for finite spaces.

### Required outputs

- Algorithm Registry with RandomSearch registration

- Seeded candidate-generation implementation

- Duplicate-prevention, reproducibility, and exhaustion tests

COMPLETION STANDARD
The same contract and seed generate the same candidate sequence, and replacing the registry entry requires no Runner or TrialRecord changes.

## WP-06 — Multi-Objective Pareto Evaluation

Owner: TBD    Reviewer: TBD    Dependencies: WP-02 and WP-04

Calculate the authoritative multi-objective result from eligible evidence without weighted scalarization or an invented universal winner.

### Included activities

- Require a finite metric for every declared objective before a trial is eligible.

- Normalize comparisons logically according to minimize or maximize direction without altering stored metrics.

- Implement dominance: no worse on every objective and strictly better on at least one.

- Return all and only non-dominated eligible TrialRecords in a deterministic ParetoFront order.

### Required outputs

- Pareto evaluator and Optimization Result

- Known mixed-direction dominance fixture

- Tests for equality, duplicates, missing objectives, dominated trials, and non-dominated trade-offs

COMPLETION STANDARD
The evaluator matches the hand-calculated expected front for the approved fixture and does not select a hidden weighted winner.

## WP-07 — Demo Worker, Reporting, and Visualization

Owner: TBD    Reviewer: TBD    Dependencies: WP-03 through WP-06

Provide a fast, reproducible demonstration and human-readable evidence that the black-box and Pareto behaviors operate end to end.

### Included activities

- Implement an external Python worker with learning_rate, temperature, batch_size, and --metrics-out arguments.

- Produce accuracy, loss, and training_time with intentional trade-offs.

- Export resolved configuration, summary, history, Pareto members, and termination reason.

- Create at least one Matplotlib view that distinguishes Pareto members from dominated trials; tabular exports remain authoritative for more than two objectives.

### Required outputs

- demo_worker.py and sample configuration

- summary.txt, history.csv, pareto_front.csv, and output plots

- Sample reproducible run directory

COMPLETION STANDARD
A clean local demonstration produces multiple trials and a nonempty, auditable Pareto Front without importing the worker into optimizer code.

## WP-08 — Verification, Integration, and Handoff

Owner: TBD    Reviewer: TBD    Dependencies: WP-01 through WP-07

Integrate the work packages into a reproducible repository and provide evidence that the baseline obligations are satisfied.

### Included activities

- Build a one-trial vertical slice before the full optimization loop.

- Add unit, integration, contract, failure, reproducibility, Pareto, and end-to-end acceptance tests.

- Document installation, configuration, command usage, output interpretation, and known exclusions.

- Verify operation without networking, concurrency, or resume behavior.

- Incorporate later course artifacts only through approved change control.

### Required outputs

- Passing verification suite and acceptance matrix

- README and repository layout

- Reproducible command-line demonstration and final handoff checklist

COMPLETION STANDARD
A reviewer can follow the README from a clean checkout, reproduce the sample result, and trace every acceptance claim to test or output evidence.

# 6. Deliverable Register

| ID | Deliverable | Required contents | Acceptance method |
| --- | --- | --- | --- |
| D-01 | Project Charter | Controlled purpose and governance baseline | Team ratification |
| D-02 | Scope of Work | Controlled work, deliverable, and acceptance baseline | Team ratification |
| D-03 | Technical Design Specification | Approved interfaces, state model, schemas, Pareto rules, and examples | Technical review |
| D-04 | Optimizer source | Controller, contracts, Runner, history, registry, RandomSearch, evaluator, and reporting | Automated tests + review |
| D-05 | Demo worker | External Python worker with controlled trade-offs and CSV output | Contract test |
| D-06 | Configuration and fixtures | Valid sample JSON, invalid cases, CSV fixtures, and hand-calculated Pareto fixture | Fixture review |
| D-07 | Verification suite | Unit, integration, failure, reproducibility, Pareto, and end-to-end tests | All required tests pass |
| D-08 | Demonstration outputs | Resolved config, history, Pareto export, summary, termination reason, and plots | Reproducible run |
| D-09 | Repository handoff | README, setup, commands, project layout, and known exclusions | Clean-checkout review |
| D-10 | Later course artifacts | Only artifacts formally required by later instructor guidance | Change-controlled |

# 7. Baseline Requirements

## 7.1 Functional requirements

| ID | Requirement |
| --- | --- |
| FR-01 | Load worker, parameter, objective, algorithm, and stop settings from JSON. |
| FR-02 | Validate the complete configuration before authorizing trial 1. |
| FR-03 | Construct the selected SearchAlgorithm through the built-in Algorithm Registry. |
| FR-04 | Use seeded RandomSearch to propose legal, previously untried Candidate Configurations. |
| FR-05 | Represent an unavailable next candidate explicitly as Search Exhaustion rather than ambiguous None. |
| FR-06 | Operate through explicit controller states and evaluate StopPolicy before every worker launch. |
| FR-07 | Execute exactly one local worker synchronously with an argument list and without shell=True. |
| FR-08 | Create a unique trial directory and pass its metrics path through --metrics-out. |
| FR-09 | Enforce the configured worker timeout and handle user cancellation and fatal errors. |
| FR-10 | Parse one CSV data row with unique metric names and finite numerical values. |
| FR-11 | Create exactly one immutable TrialRecord for every attempted worker execution. |
| FR-12 | Append TrialRecords in order and expose algorithms only to a read-only history snapshot. |
| FR-13 | Persist history after every appended trial without implementing resume behavior. |
| FR-14 | Distinguish execution success from eligibility for the complete objective vector. |
| FR-15 | Evaluate Pareto dominance using every declared objective and its direction. |
| FR-16 | Return every non-dominated eligible TrialRecord and exclude every dominated record. |
| FR-17 | Return termination reason and TrialHistory with the final Optimization Result. |
| FR-18 | Continue after recoverable worker failures until StopPolicy or Search Exhaustion stops execution. |
| FR-19 | Export resolved configuration, history, Pareto Front, summary, and visualization outputs. |
| FR-20 | Provide a demo worker and configuration with at least one maximize and one minimize objective. |

## 7.2 Non-functional requirements

| ID | Quality | Requirement |
| --- | --- | --- |
| NFR-01 | Locality | Runtime operation requires no network access, remote service, or hosted dependency. |
| NFR-02 | Sequentiality | No more than one worker process is active; no threading, async, or candidate concurrency is used. |
| NFR-03 | Reproducibility | The same valid contract, AlgorithmSpec, and seed produce the same candidate sequence. |
| NFR-04 | Modularity | Worker, algorithm, runner, history, evaluator, reporting, and stopping concerns remain replaceable at declared interfaces. |
| NFR-05 | Immutability | Contracts and completed TrialRecords cannot be mutated through public application code. |
| NFR-06 | Traceability | Every reported objective vector can be traced to parameters, metrics file, and execution status. |
| NFR-07 | Compatibility | Source targets Python 3.13.14 and avoids shell-specific command construction. |
| NFR-08 | Dependencies | Baseline dependencies remain the standard library, NumPy, pandas, and Matplotlib. |
| NFR-09 | Clarity | Public functions and domain objects use type hints, docstrings, and explicit error messages. |
| NFR-10 | Bounded scope | No resume, networking, concurrency, GUI, database, or additional search implementation is introduced. |

# 8. Acceptance and Verification

## 8.1 Acceptance scenarios

| ID | Scenario | Acceptance result |
| --- | --- | --- |
| AT-01 | Valid end-to-end run | Configured trial sequence completes and produces all required outputs. |
| AT-02 | Registry selection | RandomSearch is created by name; unknown algorithm is rejected before execution. |
| AT-03 | Reproducibility | Two runs with the same seed propose the same candidate sequence. |
| AT-04 | Finite exhaustion | A small categorical space is exhausted without duplicate looping. |
| AT-05 | Mixed-direction dominance | Hand-calculated minimize/maximize fixture returns exactly the expected front. |
| AT-06 | Pareto trade-offs | Mutually non-dominating eligible records are all retained. |
| AT-07 | Worker crash | Nonzero exit produces a failed TrialRecord and later trials continue when permitted. |
| AT-08 | Timeout | Long worker is terminated, timeout evidence is recorded, and StopPolicy is reevaluated. |
| AT-09 | Missing metrics | Missing or malformed CSV produces a traceable ineligible or failed record. |
| AT-10 | Incomplete objectives | Execution-successful record missing an objective is excluded from the Pareto Front. |
| AT-11 | Maximum trials | Controller prevents launch once the configured trial budget is consumed. |
| AT-12 | Cancellation | KeyboardInterrupt reaches finalization and preserves previously appended evidence. |
| AT-13 | No eligible trials | Optimization ends with explicit no-eligible-result status rather than a false winner. |
| AT-14 | Worker substitution | A second compliant worker runs without changes to RandomSearch or controller logic. |
| AT-15 | Strict locality | Runtime test and code review find no networking or concurrent candidate execution. |
| AT-16 | Clean checkout | Reviewer follows README and reproduces the demonstration in the supported environment. |

## 8.2 Definition of accepted MVP

- Every baseline functional and non-functional requirement is implemented or explicitly waived through change control.

- All required acceptance scenarios pass with retained evidence.

- The Pareto fixture is independently reviewable and matches the implementation output.

- The demonstration worker remains external to optimizer imports.

- The repository contains no required networking, concurrency, or resume path.

- The Charter, Scope of Work, Technical Design Specification, README, and source agree on controlling definitions.

- Team and later instructor approvals required at submission time are recorded.

# 9. Schedule, Dependencies, and Work Allocation

## 9.1 Dependency-ordered milestone plan

| ID | Milestone | Date | Exit condition |
| --- | --- | --- | --- |
| M-01 | Charter and SOW ratification | TBD | Controlled baseline approved. |
| M-02 | Technical Design approval | TBD | Interfaces, state model, schemas, and Pareto fixture approved. |
| M-03 | One-trial vertical slice | TBD | Candidate → worker → metrics → TrialRecord succeeds. |
| M-04 | Sequential loop integration | TBD | Controller, StopPolicy, registry, RandomSearch, and history operate together. |
| M-05 | Pareto result integration | TBD | Optimization Result matches the known fixture. |
| M-06 | Reporting and demo | TBD | All required output artifacts are generated. |
| M-07 | Acceptance and hardening | TBD | Required scenarios pass and defects are resolved. |
| M-08 | Submission readiness | TBD | Later course artifacts and approvals are complete. |

## 9.2 Work allocation

Assignments remain TBD. The project team will allocate each work package by recording one owner and one reviewer. A person may serve in different roles across packages, but no package is considered assigned without both entries.

| Work package | Owner | Reviewer | Allocation status |
| --- | --- | --- | --- |
| WP-01 | TBD | TBD | Unassigned |
| WP-02 | TBD | TBD | Unassigned |
| WP-03 | TBD | TBD | Unassigned |
| WP-04 | TBD | TBD | Unassigned |
| WP-05 | TBD | TBD | Unassigned |
| WP-06 | TBD | TBD | Unassigned |
| WP-07 | TBD | TBD | Unassigned |
| WP-08 | TBD | TBD | Unassigned |

## 9.3 Unresolved external dependencies

| Dependency | Current state | Scope response |
| --- | --- | --- |
| Course rubric | Unpublished or project-dependent | Add only through approved change control. |
| Final deadline | Unpublished | Populate milestone dates when issued. |
| Submission artifacts | Unpublished or project-dependent | Add required formats without silently changing technical contracts. |
| Team assignments | TBD | Ratify against the WP-01 through WP-08 matrix. |

# 10. Scope Change Control

A proposal becomes part of this Scope of Work only after its effect on work packages, deliverables, requirements, acceptance, ownership, and schedule is recorded and approved.

## 10.1 Changes requiring ratification

- adding or removing a work package, deliverable, requirement, or acceptance scenario;

- adding an algorithm implementation beyond RandomSearch;

- adding networking, concurrency, remote execution, resume, GUI, database, or hosting behavior;

- changing the JSON, command-line, CSV, TrialRecord, or Pareto-result contract;

- changing the meaning of eligibility, dominance, or termination;

- reallocating ownership after assignments are ratified; or

- incorporating later instructor requirements that materially affect scope or schedule.

## 10.2 Change procedure

- Describe the proposed change and its reason.

- Identify affected work packages, deliverables, requirements, interfaces, tests, owners, and dates.

- Classify the change as clarification, defect correction, or material scope change.

- Obtain team approval and record any instructor requirement that compelled the change.

- Update every affected controlled document before implementation becomes the new baseline.

# 11. Scope Acceptance

ACCEPTANCE EFFECT
Ratification authorizes WP-01 through WP-08 and D-01 through D-09. D-10 remains conditional on later course requirements. Ratification does not assign team work or authorize excluded capabilities.

| Team member | Decision | Date | Comments |
| --- | --- | --- | --- |
| Mel Bailey | Pending | TBD |  |
| Emily Tew | Pending | TBD |  |
| Kendahl Franklin | Pending | TBD |  |
| Charles Freeman | Pending | TBD |  |
| Will Reilly | Pending | TBD |  |